## POC
[Company Name]
Percentage of Completion Schedule
[Year End]
Entries
[8 empty] | From Inception to Date | [9 empty] | Cost Information |  |  | Billings Information |  |  | Revenue Information
Contract Number | Contract Description | Original Contract Value | Change Orders | Final Contract Amount | Estimated Cost to Complete | Estimated Profit | Estimated Profit % | Total Costs Incurred | Percent Complete | Total Revenue Recognized | Total Gross Profit | Gross Profit If Loss | Total Billings | CIE | BIE | CY Revenue Recognized | Accrued Loss | YTD Costs CY | PY Costs | Total Costs | CY Billings | PY Billings | Total Billings2 | PY Revenue | Other | Total Rev
|  |  |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Total | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on O11: Asset - Cost in Excess of Billings
Note on P11: Liability - Billings in Excess of Cost

## Example
[Company Name]
Percentage of Completion Schedule
[Year End]
Entries
[8 empty] | From Inception to Date | [9 empty] | Cost Information |  |  | Billings Information |  |  | Revenue Information
Contract Number | Contract Description | Original Contract Value | Change Orders | Final Contract Amount | Estimated Cost to Complete | Estimated Profit | Estimated Profit % | Total Costs Incurred | Percent Complete | Total Revenue Recognized | Total Gross Profit | Gross Profit If Loss | Total Billings | CIE | BIE | CY Revenue Recognized | Accrued Loss | YTD Costs CY | PY Costs | Total Costs | CY Billings | PY Billings | Total Billings2 | PY Revenue | Other | Total Rev
SS1478 | Project Loss Job | 415909 |  | 415909 | 509598 | -93689 | -22.53% | 60224.57 | 11.82% | 49152.3528 | -11072.2172 | -93689 | 120733 | 0 | -71580.6472 | 49152.3528 | -82616.7828 | 60224.57 | 0 | 60224.57 | 120733 | 0 | 120733 | 0 | 0 | 0
SS1479 | Project Profitable Job | 593951.89 |  | 593951.89 | 558320.88 | 35631.01 | 5.999% | 141190.31 | 25.29% | 150200.8155 | 9010.5055 | NA | 118389.5 | 31811.3155 | 0 | 150200.8155 | NA | 141190.31 | 0 | 141190.31 | 118389.5 | 0 | 118389.5 | 0 | 0 | 0
Total | [13 empty] | 31811.3155 | -71580.6472 | 199353.1683 | -82616.7828 | 201414.88 | 0 | 201414.88 | 239122.5 | 0 | 239122.5 | 0 | 0 | 0
Note on O11: Asset - Cost in Excess of Billings
Note on P11: Liability - Billings in Excess of Cost